ElSwedey Academy

Launch Action Plan

10 May → 8 June 2026  |  Step-by-Step Execution Guide

| Alaa ¦ Fady ¦ Aya | IATS Facebook Page | WhatsApp Groups | School Visits ¦ Internal |
| --- | --- | --- | --- |

PHASE 1 — SETUP & INFRASTRUCTURE  |  10–11 MAY

Before any public activity, all tools, pages, and groups must be ready. Complete every step below before posting anything publicly.

A. Social Media Setup

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 1 | Create the Academy's dedicated Instagram page. Username: @elswedey.academy (or similar). Add bio, profile photo, and enrollment link. | maha | Instagram |
| 2 | On the IATS school Facebook page, publish the Academy launch announcement post.Tag the Instagram page. Pin the post to the top of the page. | maha | Facebook Page |
| 3 | Create a standalone ElSwedey Academy Facebook page (separate from IATS page) for long-term brand building. Link both pages in bios. | maha | Facebook Page |
| 4 | Prepare a content folder: 10 graphics minimum before going live (logo, course cards x4, team intro x3, countdown template x2). | eman | Internal |

B. WhatsApp Groups Setup

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 5 | Create WhatsApp group: 'ElSwedey Academy — Parents'. Add school coordinators as initial members. Pin enrollment form link. | Ahmed elroby | WhatsApp |
| 6 | Create WhatsApp group: 'ElSwedey Academy — Students 11+'. For teens who register. Pin course schedule. | Ahmed elroby | WhatsApp |
| 7 | Create WhatsApp group: 'ElSwedey Academy — School Coordinators'. Add contacts from Secondary, STEM, and IATS schools. | Ahmed elroby | WhatsApp |
| 8 | Prepare a welcome message template for each group. Include: what the academy is, the 4 courses, session dates, and how to enroll. | Ahmed elroby | Internal |

C. Enrollment Setup

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 9 | Create a Google Form for enrollment: fields = Student name, Age, School name, School type, Parent phone, Course choice (dropdown). | mai | Internal |
| 10 | Test the form end-to-end. Confirm responses land in a shared Google Sheet accessible to all three engineers. | mai | Internal |
| 11 | Generate a short link for the form (use Bitly or Google short link). This is the ONE link shared everywhere. | mai | Internal |

PHASE 2 — ANNOUNCEMENT WEEK  |  12–16 MAY

This is the public launch of the brand. Goal: create buzz, grow followers, get the first WhatsApp group members.

A. Facebook (IATS Page + Academy Page)

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 1 | Day 1 post (12 May): Academy launch announcement. Include: name, tagline, the 4 courses, launch date 8 June, enrollment link. Boost with a cover graphic. | Maha | Facebook Page |
| 2 | Day 3 post (14 May): Introduce the engineering team. Photo or illustrated card of Alaa, Fady, and Aya with a 1-line bio each. | Maha | Facebook Page |
| 3 | Day 5 post (16 May): Course spotlight — Scratch. Explain what it is, who it is for (age 6-10), and what students will build. Include enrollment link. | Maha | Facebook Page |
| 4 | Share all academy posts from the IATS school page to maximise reach with the existing school audience. | Maha | Facebook Page |

B. Instagram

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 5 | Post academy announcement Reel or graphic (same day as Facebook). Add link in bio. | Fady | Instagram |
| 6 | Post Story: swipe-up poll — 'Which course are you most excited about?' (4 options = the 4 courses). | Aya | Instagram |
| 7 | Post team intro carousel (3 slides: one per engineer). Caption: 'Meet the people behind ElSwedey Academy.' | Alaa | Instagram |

C. WhatsApp

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 8 | Ask IATS school coordinator to forward the academy WhatsApp group link to ALL existing parent and student school groups. | Alaa | WhatsApp |
| 9 | Send welcome message to everyone who joins the Parents group. Include enrollment form link and course menu PDF. | Aya | WhatsApp |

PHASE 3 — SCHOOL VISITS & PARTNERSHIP ACTIVATION  |  17–25 MAY

Direct in-person outreach to Secondary, STEM, and IATS schools. Goal: confirm MOUs, collect interest lists, and get students directly into WhatsApp groups.

A. Prepare Visit Materials

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 1 | Print a 1-page flyer: Academy name, 4 courses, session structure, engineer names, launch date, QR code for enrollment form. | Team | Internal |
| 2 | Prepare a 3-minute demo on a laptop: Scratch animation sample + 30-second robot clip. Keep it visual and quick. | Fady | Internal |
| 3 | Prepare a simple MOU 1-pager for school principals: what we offer, what the school provides, and mutual benefits. | Alaa | Internal |

B. IATS School Visit  (17 May — home school, easiest first)

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 4 | Meet the school principal and coordinator. Present the academy plan. Sign or agree in principle on the MOU. | Alaa | In-Person |
| 5 | Request to present the academy to students during a free period or assembly. Run 10-minute pitch + demo. | Fady | In-Person |
| 6 | Distribute enrollment forms. Add interested students to WhatsApp group on the spot using QR code. | Aya | In-Person |
| 7 | Ask school to share announcement on their existing social media (Facebook page already confirmed). Provide them the post text + graphic. | Alaa | Facebook Page |

C. Secondary School Visit  (20–21 May)

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 8 | Contact school coordinator in advance to schedule 15-minute slot. Confirm date by 18 May. | Alaa | WhatsApp |
| 9 | Run in-school presentation: 10-min pitch, demo, distribute flyers and enrollment forms. | Fady | In-Person |
| 10 | Add interested students and parents to WhatsApp groups directly during visit. | Aya | In-Person |
| 11 | Leave printed materials with coordinator for continued sharing. Follow up by WhatsApp within 48 hours. | Team | WhatsApp |

D. STEM School Visit  (23–24 May)

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 12 | Contact STEM school coordinator. Emphasise Advanced C++ and Robotics tracks — most relevant for STEM audience. | Alaa | WhatsApp |
| 13 | Run in-school presentation tailored to STEM students: focus on robot-building and C++ problem-solving challenge. | Fady | In-Person |
| 14 | Collect registrations and add students to appropriate WhatsApp group. | Aya | In-Person |
| 15 | Post a recap on IATS Facebook page: 'We visited X school today — excited to have their students on board!' | Alaa | Facebook Page |

PHASE 4 — CONTENT & ENROLLMENT PUSH  |  25 MAY – 4 JUNE

Keep momentum. Post consistently, answer questions, and turn followers into registered students.

A. Remaining Course Spotlights

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 1 | Post: Intro to C++ spotlight — who it's for (age 11+), what they'll build, why C++ matters. Include enrollment link. | Fady | Facebook Page |
| 2 | Post: Advanced C++ spotlight — OOP, data structures, real projects. Aimed at teens 14+. | Alaa | Facebook Page |
| 3 | Post: How to Build Your Robot — the most visual course. Show a robot image, list what students learn. This post should get the most shares. | Fady | Facebook Page |
| 4 | Repost all course spotlights on Instagram as Reels or carousels with student-friendly captions. | Aya | Instagram |

B. CTA Program Announcement

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 5 | Post: Introduce your CTAs — 'Meet the student assistants who will support you between sessions.' Feature each chosen CTA with their name and a short line about them. | Aya | Facebook Page |
| 6 | In the Students and Parents WhatsApp groups, send a personal message introducing the CTAs by name. Build familiarity before sessions begin. | Alaa | WhatsApp |

C. Social Proof & Urgency

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 7 | Post: 'X students already registered!' — share enrollment numbers to create social proof. Update every 5-7 days. | Team | Facebook Page |
| 8 | Post countdown: '10 days to launch!' with a graphic showing the 4 courses and the launch date. | Fady | Facebook Page |
| 9 | In all WhatsApp groups: send a reminder about enrollment deadline. Mention that session spots are limited per course. | Aya | WhatsApp |
| 10 | Post: behind-the-scenes prep content — engineers preparing materials, CTAs in training. Humanises the brand. | Alaa | Instagram |

PHASE 5 — FINAL 3 DAYS  |  5–7 JUNE

Maximum urgency. Every channel should push enrollment. Confirm logistics for launch day.

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 1 | Post: 'Meet your engineers' — individual story or post for Alaa, Fady, and Aya. Personal tone, builds trust. | Team | Facebook Page |
| 2 | Post countdown daily: 3 days… 2 days… 1 day. Simple graphic with enrollment link each time. | Fady | Instagram |
| 3 | Send final WhatsApp broadcast to all groups: enrollment closes on 7 June. Share session link and prep checklist for Day 1. | Aya | WhatsApp |
| 4 | Contact all school coordinators: confirm final list of enrolled students from their school. Thank them personally. | Alaa | WhatsApp |
| 5 | Prepare launch day post in advance (schedule or draft): headline, course lineup, 'We are live today!' energy. | Alaa | Internal |
| 6 | Test the online session platform (Zoom/Meet/Teams). Confirm all engineers and CTAs can access and host. | Team | Internal |
| 7 | Confirm enrolled student count per course. If any course is below 8 students, do a targeted push for that course specifically. | Aya | WhatsApp |

PHASE 6 — LAUNCH DAY  |  8 JUNE 2026

| # | Action / Task | Owner | Channel |
| --- | --- | --- | --- |
| 1 | Publish launch day post on IATS Facebook page and Academy Instagram simultaneously. Tag partner schools. | Alaa | Facebook Page |
| 2 | Send 'We are live!' WhatsApp message to all groups. Include the session link and a reminder of the session time. | Aya | WhatsApp |
| 3 | Go live — engineers deliver first session. CTAs on standby for any technical issues. | Team | In-Person |
| 4 | During session: take screenshots or short clips (with student permission) for post-session content. | Fady | Internal |
| 5 | After session: post a recap — 'Day 1 done! Here is what our students built today.' Include a photo or screenshot. | Alaa | Facebook Page |
| 6 | Send post-session WhatsApp message: next session date, what to prepare, CTA support session schedule. | Aya | WhatsApp |
| 7 | Collect quick feedback from students: 1 question — 'How was your first session? Rate 1-5.' Use WhatsApp poll. | Fady | WhatsApp |

RESPONSIBILITY SUMMARY

| Owner | Primary Responsibilities |
| --- | --- |
| Alaa | Strategic lead. Oversees all channel activity. Owns Facebook posts on IATS page and Academy page. Leads school coordinator relationships and MOU negotiations. Final approval on all public content. |
| Fady | Content creation. Produces course graphics, demo materials, and visit presentations. Delivers course spotlights and behind-the-scenes posts. Manages Academy Instagram. Leads IATS and STEM school visits. |
| Aya | Community management. Owns all WhatsApp groups — creation, moderation, and broadcasts. Tracks enrollment form responses. Coordinates CTA briefing and session scheduling. Coordinates with school admins for student lists. |
| Team | Shared: enrollment form setup, session platform testing, launch day delivery, post-session feedback collection. |

Prepared for internal execution — ElSwedey Academy, May 2026